## Dashboard
Latifah's FE Auto-Generated Study Planner
The plan adjusts itself. Edit YELLOW cells (inputs + daily availability + Topic Planner). Read GREEN cells. Open Weekly Plan tab to see today's auto-generated task.
EXAM DATE |  | DAYS REMAINING |  | WEEKS REMAINING |  |  | PROGRESS % |  | READINESS |  | NEXT BEST TOPIC
2026-07-31 |  | 74 |  | 10.6 |  |  | 0% |  | 0% |  | 6.4 Waveform Analysis
COMPLETED HOURS |  | REMAINING HOURS |  | WEEKLY AVAILABLE |  |  | WEEKLY PLANNED |  | HIGH-PRIORITY REMAINING |  | THIS WEEK
0 |  | 150.5 |  | 3.8 |  |  | 3.8 |  | 37 |  | 0 / 7 done
What Should I Study Next? - Today is Monday, May 18
Today's Auto-Topic |  |  | 6.6 Impedance
Today's Auto-Task |  |  | Review formulas, then practice short FE-style problems. Topic: 6.6 Impedance
Today's Mode + Length |  |  | Normal - 35 minutes
Next Best Topic Overall |  |  | 6.4 Waveform Analysis (Circuit Analysis, priority 7.35)
Why This Topic |  |  | High exam weight - core scoring chapter
Low-Energy Backup |  |  | Try: FE Handbook formula lookup - 10-15 min
Essential Inputs |  |  | Daily Availability (drives the planner) |  |  |  |  | Weekly Plan Preview
|  |  | Day | Min | Energy | Mode |  | Day | Auto Topic | Auto Task |  | Min | Done
Student Name | Latifah |  | Sunday | 30 | 2 | Normal |  | Sunday | 6.4 Waveform Analysis | Study the core concept, then solve 2-4 examples. Topic: 6.4 Waveform Analysis |  | 30 | No
Exam Date | 2026-07-31 |  | Monday | 35 | 3 | Normal |  | Monday | 6.6 Impedance | Review formulas, then practice short FE-style problems. Topic: 6.6 Impedance |  | 35 | No
Start Date | 2026-05-18 |  | Tuesday | 30 | 2 | Normal |  | Tuesday | 6.5 Phasors | Focus on common mistakes and update confidence. Topic: 6.5 Phasors |  | 30 | No
Study Style | Flexible |  | Wednesday | 35 | 3 | Normal |  | Wednesday | 6.3 Thevenin and Norton Theorems | Study the core concept, then solve 2-4 examples. Topic: 6.3 Thevenin and Norton Theorems |  | 35 | No
Min Wkly Hrs | 5 |  | Thursday | 25 | 2 | Low Energy |  | Thursday |  | FE Handbook formula lookup - 10-15 min |  | 20 | No
Max Wkly Hrs | 10 |  | Friday | 30 | 3 | Family |  | Friday | 13.1 Communication Theory | Light review of 13.1 Communication Theory. No heavy problem solving. |  | 30 | No
|  |  | Saturday | 45 | 4 | Family |  | Saturday | 8.1 Sampling | Light review of 8.1 Sampling. No heavy problem solving. |  | 45 | No
Visual Progress
Study Modes Reference
Normal Mode (25-45 min) |  |  | 5 min concept + 20-30 min problems + 5 min correction/log | [5 empty] | Sun-Thu after work
Low-Energy Mode (10-20 min) |  |  | Formula lookup + 1-2 examples + flashcards or mistake review | [5 empty] | Tired evenings - keeps streak alive
Family Mode (20-45 min if available) |  |  | Light review or mini quiz only - no heavy new theory | [5 empty] | Friday/Saturday
Rest (0 min) |  |  | No study required. Recover. | [5 empty] | Whenever you need it - never punished

## Topic Planner
Include? | FE Section | Topic / Problem Set | Q Range | Avg Wt | Tier | Confidence | Difficulty | Boredom | Quick Win | Priority Score | Recommended Depth | Suggested Hrs | Completed Hrs | Progress % | Status | Next Action | Notes
Yes | Mathematics | 1.1 Algebra and Trigonometry | 11-17 | 14 | 1 | 3 | 2 | 2 | 4 | 7.1 | Standard Study | 3 | 0 | 0% | Not Started | Study Next | Foundation - quick warm-up sessions | 7.1 | 9 | 2.9 | 2e-05
Yes | Mathematics | 1.2 Complex Numbers | 11-17 | 14 | 1 | 3 | 2 | 2 | 5 | 7.3 | Deep Study | 2.5 | 0 | 0% | Not Started | Study Next | CRITICAL for AC circuits and phasors | 7.3 | 11 | 2.7 | 3e-05
Yes | Mathematics | 1.3 Discrete Math & Progressions | 11-17 | 14 | 1 | 2 | 2 | 2 | 3 | 7.15 | Fast Review | 1 | 0 | 0% | Not Started | Study Next | Lower-yield within math chapter | 7.15 | 7 | 2.85 | 4e-05
Yes | Mathematics | 1.4 Analytic Geometry | 11-17 | 14 | 1 | 2 | 2 | 3 | 2 | 6.9 | Light Review | 1 | 0 | 0% | Not Started | Study Next | Conics rare on exam | 6.9001 | 4 | 3.1 | 5e-05
Yes | Mathematics | 1.5 Calculus | 11-17 | 14 | 1 | 2 | 3 | 3 | 4 | 7.3 | Standard Study | 3 | 0 | 0% | Not Started | Study Next | Derivatives + integrals appear often | 7.3001 | 7.0001 | 2.7001 | 6e-05
Yes | Mathematics | 1.6 Differential Equations | 11-17 | 14 | 1 | 2 | 4 | 4 | 3 | 7.05 | Standard Study | 2.5 | 0 | 0% | Not Started | Study Next | Heavy - split into 2 sessions | 7.0501 | 3.0001 | 2.9501 | 7e-05
Yes | Mathematics | 1.7 Matrix and Vector Analysis | 11-17 | 14 | 1 | 2 | 3 | 3 | 3 | 7.1 | Standard Study | 2 | 0 | 0% | Not Started | Study Next | Linear algebra basics | 7.1001 | 5.0001 | 2.9001 | 8e-05
Yes | Probability and Statistics | 2.1 Central Tendencies & Dispersions | 4-6 | 5 | 2 | 3 | 2 | 2 | 4 | 3.65 | Fast Review | 1 | 0 | 0% | Not Started | Practice | Calculator-fast - quick win | 3.6501 | 9.0001 | 6.3501 | 5.4001
Yes | Probability and Statistics | 2.2 Permutation, Combination, Probability | 4-6 | 5 | 2 | 2 | 3 | 2 | 3 | 3.7 | Standard Study | 1.5 | 0 | 0% | Not Started | Practice | Watch combination vs permutation | 3.7001 | 6.0001 | 6.3001 | 4.2001
Yes | Probability and Statistics | 2.3 Probability Distributions | 4-6 | 5 | 2 | 2 | 3 | 3 | 3 | 3.65 | Standard Study | 1.5 | 0 | 0% | Not Started | Practice | Normal + binomial - use handbook tables | 3.6501 | 5.0001 | 6.3501 | 3.7001
Yes | Probability and Statistics | 2.4 Expected Values | 4-6 | 5 | 2 | 3 | 2 | 2 | 4 | 3.65 | Fast Review | 1 | 0 | 0% | Not Started | Practice | Quick win with weighted-sum | 3.6501 | 9.0001 | 6.3501 | 5.4001
Yes | Ethics and Professional Practice | 3.1 Code of Ethics & NCEES Model Law | 4-6 | 5 | 1 | 3 | 1 | 2 | 5 | 4.15 | Standard Study | 1.5 | 0 | 0% | Not Started | Practice | Public welfare beats everything | 4.1501 | 12.0001 | 5.8501 | 0.00013
Yes | Ethics and Professional Practice | 3.2 Intellectual Property | 4-6 | 5 | 1 | 3 | 1 | 2 | 5 | 4.15 | Fast Review | 1 | 0 | 0% | Not Started | Practice | Memorize patent / trademark / copyright / trade secret | 4.1501 | 12.0001 | 5.8501 | 0.00014
Yes | Ethics and Professional Practice | 3.3 Safety | 4-6 | 5 | 1 | 3 | 1 | 2 | 5 | 4.15 | Fast Review | 1 | 0 | 0% | Not Started | Practice | PPE, hazard vs risk | 4.1502 | 12.0001 | 5.8501 | 0.00015
Yes | Engineering Economics | 4.1 Time Value of Money | 5-8 | 7 | 1 | 2 | 2 | 2 | 5 | 5.1 | Deep Study | 3 | 0 | 0% | Not Started | Study This Week | Use FE handbook factor tables | 5.1002 | 11.0002 | 4.9002 | 0.00016
Yes | Engineering Economics | 4.2 Cost Estimation | 5-8 | 7 | 1 | 2 | 2 | 3 | 4 | 4.85 | Standard Study | 1.5 | 0 | 0% | Not Started | Study This Week | Fixed vs variable cost basics | 4.8502 | 8.0002 | 5.1502 | 0.00017
Yes | Engineering Economics | 4.3 Risk Identification & Analysis | 5-8 | 7 | 1 | 2 | 2 | 3 | 3 | 4.65 | Fast Review | 1 | 0 | 0% | Not Started | Study This Week | Break-even, expected value | 4.6502 | 6.0002 | 5.3502 | 0.00018
Yes | Properties of Electrical Materials | 5.1 Electrical Properties | 4-6 | 5 | 3 | 2 | 3 | 4 | 2 | 3.1 | Light Review | 1 | 0 | 0% | Not Started | Practice | Memorize key terms only | 3.1002 | 2.0002 | 6.9002 | 2.2002
Yes | Properties of Electrical Materials | 5.2 Thermal Properties | 4-6 | 5 | 3 | 2 | 2 | 3 | 3 | 3.35 | Light Review | 0.5 | 0 | 0% | Not Started | Practice | Temperature coefficient drill only | 3.3502 | 6.0002 | 6.6502 | 4.2002
Yes | Circuit Analysis | 6.1 Kirchhoff Laws (KCL/KVL) | 11-17 | 14 | 1 | 2 | 3 | 3 | 4 | 7.3 | Deep Study | 3 | 0 | 0% | Not Started | Study Next | Master node and mesh - core skill | 7.3002 | 7.0002 | 2.7002 | 0.00021
Yes | Circuit Analysis | 6.2 Series and Parallel Equivalent Circuits | 11-17 | 14 | 1 | 3 | 2 | 2 | 5 | 7.3 | Standard Study | 2 | 0 | 0% | Not Started | Study Next | Voltage and current divider | 7.3002 | 11.0002 | 2.7002 | 0.00022
Yes | Circuit Analysis | 6.3 Thevenin and Norton Theorems | 11-17 | 14 | 1 | 2 | 3 | 3 | 4 | 7.3 | Deep Study | 3 | 0 | 0% | Not Started | Study Next | Source transformation + max power transfer | 7.3002 | 7.0002 | 2.7002 | 0.00023
Yes | Circuit Analysis | 6.4 Waveform Analysis | 11-17 | 14 | 1 | 2 | 2 | 2 | 4 | 7.35 | Standard Study | 2 | 0 | 0% | Not Started | Study Next | RMS, average, peak | 7.3502 | 9.0002 | 2.6502 | 0.00024
Yes | Circuit Analysis | 6.5 Phasors | 11-17 | 14 | 1 | 2 | 3 | 3 | 4 | 7.3 | Standard Study | 2.5 | 0 | 0% | Not Started | Study Next | Polar to rectangular conversion | 7.3003 | 7.0003 | 2.7003 | 0.00025
Yes | Circuit Analysis | 6.6 Impedance | 11-17 | 14 | 1 | 2 | 3 | 3 | 4 | 7.3 | Deep Study | 3 | 0 | 0% | Not Started | Study Next | R, L, C impedance + AC steady-state | 7.3003 | 7.0003 | 2.7003 | 0.00026
Yes | Linear Systems | 7.1 Frequency and Transient Response | 5-8 | 7 | 2 | 2 | 4 | 4 | 3 | 4.3 | Standard Study | 2.5 | 0 | 0% | Not Started | Practice | Time constant, step response | 4.3003 | 3.0003 | 5.7003 | 2.7003
Yes | Linear Systems | 7.2 Resonance | 5-8 | 7 | 2 | 2 | 3 | 3 | 3 | 4.35 | Standard Study | 2 | 0 | 0% | Not Started | Practice | f0, Q factor, bandwidth | 4.3503 | 5.0003 | 5.6503 | 3.7003
Yes | Linear Systems | 7.3 Laplace Transform | 5-8 | 7 | 2 | 2 | 4 | 4 | 3 | 4.3 | Standard Study | 2.5 | 0 | 0% | Not Started | Practice | Use handbook table - heavy | 4.3003 | 3.0003 | 5.7003 | 2.7003
Yes | Linear Systems | 7.4 Transfer Functions | 5-8 | 7 | 2 | 2 | 4 | 3 | 3 | 4.35 | Standard Study | 2 | 0 | 0% | Not Started | Practice | Poles, zeros, stability | 4.3503 | 4.0003 | 5.6503 | 3.2003
Yes | Signal Processing | 8.1 Sampling | 5-8 | 7 | 2 | 2 | 2 | 2 | 4 | 4.6 | Standard Study | 1.5 | 0 | 0% | Not Started | Study This Week | Nyquist - quick win | 4.6003 | 9.0003 | 5.4003 | 5.7003
Yes | Signal Processing | 8.2 Analog Filters | 5-8 | 7 | 2 | 2 | 3 | 3 | 3 | 4.35 | Standard Study | 2 | 0 | 0% | Not Started | Practice | Filter type identification | 4.3503 | 5.0003 | 5.6503 | 3.7003
Yes | Signal Processing | 8.3 Digital Filters & Z-Transforms | 5-8 | 7 | 2 | 2 | 4 | 4 | 2 | 4.1 | Fast Review | 1.5 | 0 | 0% | Not Started | Practice | Heavy - keep light | 4.1003 | 1.0003 | 5.9003 | 1.7003
Yes | Signal Processing | 8.4 Continuous Time Convolution | 5-8 | 7 | 2 | 2 | 4 | 4 | 2 | 4.1 | Fast Review | 1.5 | 0 | 0% | Not Started | Practice | Recognize patterns only | 4.1003 | 1.0003 | 5.9003 | 1.7003
Yes | Signal Processing | 8.5 Discrete Time Convolution | 5-8 | 7 | 2 | 2 | 4 | 4 | 2 | 4.1 | Fast Review | 1 | 0 | 0% | Not Started | Practice | Table approach | 4.1003 | 1.0004 | 5.9004 | 1.7004
Yes | Electronics | 9.1 Semiconductor Materials | 7-11 | 9 | 1 | 2 | 2 | 3 | 3 | 5.35 | Standard Study | 1.5 | 0 | 0% | Not Started | Study This Week | Doping, p-n basics | 5.3504 | 6.0004 | 4.6504 | 0.00036
Yes | Electronics | 9.2 Diodes and Thyristors | 7-11 | 9 | 1 | 2 | 2 | 2 | 4 | 5.6 | Deep Study | 2.5 | 0 | 0% | Not Started | Study This Week | Diode model + rectifiers | 5.6004 | 9.0004 | 4.4004 | 0.00037
Yes | Electronics | 9.3 Bipolar Junction Transistors (BJTs) | 7-11 | 9 | 1 | 2 | 4 | 3 | 3 | 5.35 | Standard Study | 2.5 | 0 | 0% | Not Started | Study This Week | Active vs saturation - heavy | 5.3504 | 4.0004 | 4.6504 | 0.00038
Yes | Electronics | 9.4 JFETs | 7-11 | 9 | 1 | 2 | 3 | 3 | 2 | 5.15 | Fast Review | 1 | 0 | 0% | Not Started | Study This Week | Lower priority - quick pass | 5.1504 | 3.0004 | 4.8504 | 0.00039
Yes | Electronics | 9.5 MOSFETs | 7-11 | 9 | 1 | 2 | 3 | 3 | 3 | 5.35 | Standard Study | 2 | 0 | 0% | Not Started | Study This Week | Region of operation | 5.3504 | 5.0004 | 4.6504 | 0.0004
Yes | Electronics | 9.6 Operational Amplifiers | 7-11 | 9 | 1 | 2 | 2 | 2 | 5 | 5.8 | Deep Study | 3 | 0 | 0% | Not Started | Study This Week | HUGE high yield - virtual short rule | 5.8004 | 11.0004 | 4.2004 | 0.00041
Yes | Electronics | 9.7 Power Electronics | 7-11 | 9 | 1 | 2 | 3 | 3 | 3 | 5.35 | Standard Study | 2 | 0 | 0% | Not Started | Study This Week | Rectifier, inverter, chopper basics | 5.3504 | 5.0004 | 4.6504 | 0.00042
Yes | Electronics | 9.8 Instrumentation | 7-11 | 9 | 1 | 3 | 2 | 3 | 3 | 5.1 | Fast Review | 1 | 0 | 0% | Not Started | Study This Week | Accuracy vs precision vs resolution | 5.1004 | 6.0004 | 4.9004 | 0.00043
Yes | Power Systems | 10.1 Power Theory & Single-Phase Power | 8-12 | 10 | 1 | 3 | 2 | 2 | 5 | 5.9 | Deep Study | 3 | 0 | 0% | Not Started | Study This Week | Power triangle - core skill | 5.9004 | 11.0004 | 4.1004 | 0.00044
Yes | Power Systems | 10.2 Three-Phase Power | 8-12 | 10 | 1 | 2 | 3 | 3 | 4 | 5.9 | Deep Study | 3 | 0 | 0% | Not Started | Study This Week | Wye vs Delta + sqrt(3) factor | 5.9005 | 7.0004 | 4.1004 | 0.00045
Yes | Power Systems | 10.3 Power Factor | 8-12 | 10 | 1 | 3 | 2 | 2 | 5 | 5.9 | Standard Study | 2 | 0 | 0% | Not Started | Study This Week | PF correction with capacitors | 5.9005 | 11.0005 | 4.1005 | 0.00046
Yes | Power Systems | 10.4 Voltage Regulation & Voltage Drop | 8-12 | 10 | 1 | 2 | 2 | 3 | 3 | 5.7 | Standard Study | 1.5 | 0 | 0% | Not Started | Study This Week | Per-unit basics | 5.7005 | 6.0005 | 4.3005 | 0.00047
Yes | Power Systems | 10.5 Transformers | 8-12 | 10 | 1 | 2 | 3 | 3 | 4 | 5.9 | Standard Study | 2.5 | 0 | 0% | Not Started | Study This Week | Turns ratio + reflected impedance | 5.9005 | 7.0005 | 4.1005 | 0.00048
Yes | Power Systems | 10.6 Motors and Generators | 8-12 | 10 | 1 | 2 | 3 | 3 | 4 | 5.9 | Standard Study | 2.5 | 0 | 0% | Not Started | Study This Week | Slip + synchronous speed | 5.9005 | 7.0005 | 4.1005 | 0.00049
Yes | Electromagnetics | 11.1 Electrostatics | 4-6 | 5 | 3 | 2 | 4 | 4 | 2 | 3.1 | Light Review | 1.5 | 0 | 0% | Not Started | Practice | E-field formulas only | 3.1005 | 1.0005 | 6.9005 | 1.7005
Yes | Electromagnetics | 11.2 Magnetostatics | 4-6 | 5 | 3 | 2 | 4 | 4 | 2 | 3.1 | Light Review | 1 | 0 | 0% | Not Started | Practice | Right-hand rule + B-field | 3.1005 | 1.0005 | 6.9005 | 1.7005
Yes | Electromagnetics | 11.3 Electrodynamics & Maxwell's Equations | 4-6 | 5 | 3 | 1 | 5 | 5 | 1 | 3.1 | Skip Unless Time | 0.5 | 0 | 0% | Not Started | Practice | Recognition only - hardest topic | 3.1005 | -2.9995 | 6.9005 | 0.00052
Yes | Electromagnetics | 11.4 Wave Propagation | 4-6 | 5 | 3 | 2 | 4 | 4 | 2 | 3.1 | Light Review | 1 | 0 | 0% | Not Started | Practice | Frequency-wavelength-velocity | 3.1005 | 1.0005 | 6.9005 | 1.7005
Yes | Electromagnetics | 11.5 Transmission Lines | 4-6 | 5 | 3 | 2 | 4 | 4 | 2 | 3.1 | Light Review | 1 | 0 | 0% | Not Started | Practice | Z0 + reflection coefficient only | 3.1005 | 1.0005 | 6.9005 | 1.7005
Yes | Control Systems | 12.1 Block Diagrams & Closed/Open-Loop | 6-9 | 8 | 2 | 2 | 3 | 3 | 4 | 4.9 | Standard Study | 2.5 | 0 | 0% | Not Started | Study This Week | Block reduction technique | 4.9005 | 7.0005 | 5.1005 | 4.7005
Yes | Control Systems | 12.2 Bode Plots | 6-9 | 8 | 2 | 2 | 3 | 3 | 3 | 4.7 | Standard Study | 2 | 0 | 0% | Not Started | Study This Week | Slope rules from poles/zeros | 4.7006 | 5.0006 | 5.3006 | 3.7006
Yes | Control Systems | 12.3 System Stability & Frequency Response | 6-9 | 8 | 2 | 2 | 4 | 3 | 3 | 4.7 | Standard Study | 2 | 0 | 0% | Not Started | Study This Week | Pole location -> stability | 4.7006 | 4.0006 | 5.3006 | 3.2006
Yes | Control Systems | 12.4 Controller Performance | 6-9 | 8 | 2 | 2 | 3 | 3 | 3 | 4.7 | Standard Study | 2 | 0 | 0% | Not Started | Study This Week | Settling time, overshoot, PID | 4.7006 | 5.0006 | 5.3006 | 3.7006
Yes | Communications | 13.1 Communication Theory | 5-8 | 7 | 2 | 2 | 2 | 2 | 4 | 4.6 | Standard Study | 1.5 | 0 | 0% | Not Started | Study This Week | SNR, bandwidth, channel capacity | 4.6006 | 9.0006 | 5.4006 | 5.7006
Yes | Communications | 13.2 Amplitude Modulation | 5-8 | 7 | 2 | 2 | 3 | 3 | 3 | 4.35 | Standard Study | 1.5 | 0 | 0% | Not Started | Practice | AM index + bandwidth = 2*fm | 4.3506 | 5.0006 | 5.6506 | 3.7006
Yes | Communications | 13.3 Angle Modulation (FM/PM) | 5-8 | 7 | 2 | 2 | 3 | 3 | 3 | 4.35 | Standard Study | 1.5 | 0 | 0% | Not Started | Practice | FM/PM + Carson's rule | 4.3506 | 5.0006 | 5.6506 | 3.7006
Yes | Communications | 13.4 Fourier Transforms | 5-8 | 7 | 2 | 2 | 4 | 4 | 3 | 4.3 | Standard Study | 2 | 0 | 0% | Not Started | Practice | Use handbook pairs | 4.3006 | 3.0006 | 5.7006 | 2.7006
Yes | Communications | 13.5 Digital Communications | 5-8 | 7 | 2 | 2 | 3 | 3 | 3 | 4.35 | Standard Study | 1.5 | 0 | 0% | Not Started | Practice | PCM, bit rate, quantization | 4.3506 | 5.0006 | 5.6506 | 3.7006
Yes | Communications | 13.6 Multiplexing | 5-8 | 7 | 2 | 3 | 2 | 2 | 3 | 4.15 | Fast Review | 1 | 0 | 0% | Not Started | Practice | TDM/FDM/CDM compare - quick | 4.1506 | 7.0006 | 5.8506 | 4.4006
Yes | Computer Networks | 14.1 Routing and Switching | 4-6 | 5 | 3 | 2 | 2 | 2 | 3 | 3.4 | Fast Review | 1 | 0 | 0% | Not Started | Practice | Layer 2 vs 3 | 3.4006 | 7.0007 | 6.6006 | 4.7007
Yes | Computer Networks | 14.2 Network Topologies & Models | 4-6 | 5 | 3 | 3 | 2 | 2 | 4 | 3.35 | Fast Review | 1 | 0 | 0% | Not Started | Practice | OSI 7 layers - memorize | 3.3507 | 9.0007 | 6.6507 | 5.4007
Yes | Computer Networks | 14.3 IP Addressing (IPv4/IPv6) | 4-6 | 5 | 3 | 2 | 3 | 3 | 3 | 3.35 | Standard Study | 1.5 | 0 | 0% | Not Started | Practice | Subnetting calculation | 3.3507 | 5.0007 | 6.6507 | 3.7007
Yes | Computer Networks | 14.4 Protocols (TCP/UDP/ICMP) | 4-6 | 5 | 3 | 3 | 2 | 2 | 3 | 3.15 | Fast Review | 1 | 0 | 0% | Not Started | Practice | TCP vs UDP comparison | 3.1507 | 7.0007 | 6.8507 | 4.4007
Yes | Computer Networks | 14.5 Network Security | 4-6 | 5 | 3 | 3 | 2 | 2 | 3 | 3.15 | Fast Review | 1 | 0 | 0% | Not Started | Practice | CIA triad + firewall basics | 3.1507 | 7.0007 | 6.8507 | 4.4007
Yes | Digital Systems | 15.1 Number Systems | 8-12 | 10 | 1 | 3 | 2 | 2 | 5 | 5.9 | Standard Study | 2 | 0 | 0% | Not Started | Study This Week | Binary, hex, two's complement | 5.9007 | 11.0007 | 4.1007 | 0.0007
Yes | Digital Systems | 15.2 Boolean Logic | 8-12 | 10 | 1 | 3 | 2 | 2 | 5 | 5.9 | Standard Study | 2 | 0 | 0% | Not Started | Study This Week | De Morgan + simplification | 5.9007 | 11.0007 | 4.1007 | 0.00071
Yes | Digital Systems | 15.3 Logic Gates and Circuits | 8-12 | 10 | 1 | 3 | 2 | 2 | 4 | 5.7 | Standard Study | 2 | 0 | 0% | Not Started | Study This Week | Truth table -> expression | 5.7007 | 9.0007 | 4.3007 | 0.00072
Yes | Digital Systems | 15.4 Logic Minimization (K-Maps, SOP, POS) | 8-12 | 10 | 1 | 2 | 3 | 3 | 4 | 5.9 | Standard Study | 2.5 | 0 | 0% | Not Started | Study This Week | Practice grouping rules | 5.9007 | 7.0007 | 4.1007 | 0.00073
Yes | Digital Systems | 15.5 Sequential Circuits & Counters | 8-12 | 10 | 1 | 2 | 3 | 3 | 4 | 5.9 | Standard Study | 2.5 | 0 | 0% | Not Started | Study This Week | Flip-flop characteristic table | 5.9007 | 7.0007 | 4.1007 | 0.00074
Yes | Digital Systems | 15.6 Combinational Circuits | 8-12 | 10 | 1 | 2 | 3 | 3 | 3 | 5.7 | Standard Study | 2 | 0 | 0% | Not Started | Study This Week | MUX, decoder, encoder | 5.7008 | 5.0008 | 4.3007 | 0.00075
Yes | Digital Systems | 15.7 Programmable Logic Devices | 8-12 | 10 | 1 | 2 | 2 | 3 | 2 | 5.5 | Fast Review | 1 | 0 | 0% | Not Started | Study This Week | PLA/PAL/FPGA - lighter | 5.5008 | 4.0008 | 4.5008 | 0.00076
Yes | Digital Systems | 15.8 State Machine Design | 8-12 | 10 | 1 | 2 | 4 | 3 | 3 | 5.7 | Standard Study | 2.5 | 0 | 0% | Not Started | Study This Week | Mealy vs Moore | 5.7008 | 4.0008 | 4.3008 | 0.00077
Yes | Digital Systems | 15.9 Timing | 8-12 | 10 | 1 | 2 | 3 | 3 | 3 | 5.7 | Standard Study | 1.5 | 0 | 0% | Not Started | Study This Week | Setup/hold + fmax | 5.7008 | 5.0008 | 4.3008 | 0.00078
Yes | Computer Systems | 16.1 Microprocessor | 5-8 | 7 | 2 | 2 | 3 | 3 | 3 | 4.35 | Standard Study | 2 | 0 | 0% | Not Started | Practice | Registers + instruction cycle | 4.3508 | 5.0008 | 5.6508 | 3.7008
Yes | Computer Systems | 16.2 Memory Technology and Systems | 5-8 | 7 | 2 | 3 | 2 | 2 | 4 | 4.35 | Standard Study | 2 | 0 | 0% | Not Started | Practice | Address bus size calculation | 4.3508 | 9.0008 | 5.6508 | 5.4008
Yes | Computer Systems | 16.3 Architecture and Interfacing | 5-8 | 7 | 2 | 2 | 3 | 3 | 3 | 4.35 | Fast Review | 1.5 | 0 | 0% | Not Started | Practice | Memory-mapped I/O | 4.3508 | 5.0008 | 5.6508 | 3.7008
Yes | Software Engineering | 17.1 Algorithms - Complexity & Big-O | 4-6 | 5 | 2 | 3 | 2 | 2 | 4 | 3.65 | Standard Study | 1.5 | 0 | 0% | Not Started | Practice | Identify O(n), O(log n), etc. | 3.6508 | 9.0008 | 6.3508 | 5.4008
Yes | Software Engineering | 17.2 Algorithms - Sorting and Searching | 4-6 | 5 | 2 | 3 | 2 | 2 | 4 | 3.65 | Standard Study | 1.5 | 0 | 0% | Not Started | Practice | Binary search + complexity table | 3.6508 | 9.0008 | 6.3508 | 5.4008
Yes | Software Engineering | 17.3 Linear Data Structures | 4-6 | 5 | 2 | 3 | 2 | 2 | 3 | 3.45 | Fast Review | 1 | 0 | 0% | Not Started | Practice | FIFO vs LIFO basics | 3.4508 | 7.0008 | 6.5508 | 4.4008
Yes | Software Engineering | 17.4 Trees and Graphs | 4-6 | 5 | 2 | 2 | 3 | 3 | 2 | 3.45 | Fast Review | 1.5 | 0 | 0% | Not Started | Practice | BFS vs DFS | 3.4508 | 3.0008 | 6.5508 | 2.7008
Yes | Software Engineering | 17.5 Software Design & Testing | 4-6 | 5 | 2 | 3 | 2 | 3 | 3 | 3.4 | Fast Review | 1 | 0 | 0% | Not Started | Practice | SDLC + test types | 3.4009 | 6.0009 | 6.6009 | 3.9009

## Weekly Plan
Weekly Plan - Auto-Generated
This plan is generated automatically from the Topic Planner priorities + your Dashboard daily availability. Edit only the YELLOW cells (Done?, Actual Min, Notes). To change the plan, change Confidence/Include in Topic Planner or Mode/Minutes/Energy on the Dashboard.
A. This Week's Plan
Date | Day | Mode | Avail Min | Auto Topic | Auto Task | Sugg Min | Done? | Actual Min | Notes
2026-05-17 | Sunday | Normal | 30 | 6.4 Waveform Analysis | Study the core concept, then solve 2-4 examples. Topic: 6.4 Waveform Analysis | 30 | No | 0
2026-05-18 | Monday | Normal | 35 | 6.6 Impedance | Review formulas, then practice short FE-style problems. Topic: 6.6 Impedance | 35 | No | 0
2026-05-19 | Tuesday | Normal | 30 | 6.5 Phasors | Focus on common mistakes and update confidence. Topic: 6.5 Phasors | 30 | No | 0
2026-05-20 | Wednesday | Normal | 35 | 6.3 Thevenin and Norton Theorems | Study the core concept, then solve 2-4 examples. Topic: 6.3 Thevenin and Norton Theorems | 35 | No | 0
2026-05-21 | Thursday | Low Energy | 25 |  | FE Handbook formula lookup - 10-15 min | 20 | No | 0
2026-05-22 | Friday | Family | 30 | 13.1 Communication Theory | Light review of 13.1 Communication Theory. No heavy problem solving. | 30 | No | 0
2026-05-23 | Saturday | Family | 45 | 8.1 Sampling | Light review of 8.1 Sampling. No heavy problem solving. | 45 | No | 0
|  |  | Totals |  |  | 225 | 0 / 7 | 0
B. Week Capacity & Health
Available Hours |  | Planned Hours |  | Done Hours |  | Capacity Status
3.8 |  | 3.8 |  | 0 |  | Balanced
C. Weekly Reflection (Sunday 5-min check-in)
What worked this week?
What was difficult?
Which topic needs more time?
What is next week's focus?

## _Lists (hidden)
| Low-Energy Tasks | Normal Task Templates | Family Task Templates | WeekdayNum | DayName | Status | Order
1 | FE Handbook formula lookup - 10-15 min | Study the core concept, then solve 2-4 examples. | Optional light review only. | 1 | Sunday | Not Started | 1
2 | Review one solved example - 10-20 min | Review formulas, then practice short FE-style problems. | One short review or mini quiz if time allows. | 2 | Monday | Learning | 2
3 | Mistake review of last topic - 15-20 min | Focus on common mistakes and update confidence. | Catch-up only. Do not start a heavy new topic. | 3 | Tuesday | Practicing | 3
4 | Flashcard review - 10-15 min |  |  | 4 | Wednesday | Improving | 4
5 | Light Ethics review (3.1, 3.2, 3.3) - 15-20 min |  |  | 5 | Thursday | Strong | 5
6 | Engineering Economics formula drill - 15-25 min |  |  | 6 | Friday | Exam Ready | 6
|  |  |  | 7 | Saturday | Skipped | 7

## _Calc (hidden)
OVERALL PROGRESS
Completed Hours | 0
Remaining Hours | 150.5
STATUS BREAKDOWN
Not Started | 85
Learning | 0
Practicing | 0
Improving | 0
Strong | 0
Exam Ready | 0
Skipped | 0
TOP 5 TOPICS | Topic | Score | Section
1 | 6.4 Waveform Analysis | 7.35 | Circuit Analysis
2 | 6.6 Impedance | 7.3 | Circuit Analysis
3 | 6.5 Phasors | 7.3 | Circuit Analysis
4 | 6.3 Thevenin and Norton Theorems | 7.3 | Circuit Analysis
5 | 6.2 Series and Parallel Equivalent Circuits | 7.3 | Circuit Analysis
AGGREGATES
Total Topics Included | 85
High Priority Remaining | 37
Total Planned Hours | 150.5
Total Completed Hours | 0
Remaining Suggested Hours | 150.5
Overall Progress % | 0%
Readiness Score % | 0%
TIER PROGRESS
Tier | Done | Remaining
Tier 1 | 0 | 87.5
Tier 2 | 0 | 51
Tier 3 | 0 | 12
WEEKLY HOURS
Category | Hours
Available | 3.8
Planned | 3.8

## _PlanEngine (hidden)
DayIdx | Date | DayName | Mode | AvailMins | Energy | NormalRank | LowEnergyRank | FamilyRank | TopicIdx | TopicName | TopicSection | TopicTier | SuggestedMins | AutoTask | TooMuch | TooLittle
1 | 2026-05-17 | Sunday | Normal | 30 | 2 | 1 | 0 | 0 | 23 | 6.4 Waveform Analysis | Circuit Analysis | 1 | 30 | Study the core concept, then solve 2-4 examples. Topic: 6.4 Waveform Analysis | 0 | 0
2 | 2026-05-18 | Monday | Normal | 35 | 3 | 2 | 0 | 0 | 25 | 6.6 Impedance | Circuit Analysis | 1 | 35 | Review formulas, then practice short FE-style problems. Topic: 6.6 Impedance | 0 | 0
3 | 2026-05-19 | Tuesday | Normal | 30 | 2 | 3 | 0 | 0 | 24 | 6.5 Phasors | Circuit Analysis | 1 | 30 | Focus on common mistakes and update confidence. Topic: 6.5 Phasors | 0 | 0
4 | 2026-05-20 | Wednesday | Normal | 35 | 3 | 4 | 0 | 0 | 22 | 6.3 Thevenin and Norton Theorems | Circuit Analysis | 1 | 35 | Study the core concept, then solve 2-4 examples. Topic: 6.3 Thevenin and Norton Theorems | 0 | 0
5 | 2026-05-21 | Thursday | Low Energy | 25 | 2 | 0 | 1 | 0 | 0 |  |  |  | 20 | FE Handbook formula lookup - 10-15 min | 0 | 0
6 | 2026-05-22 | Friday | Family | 30 | 3 | 0 | 0 | 1 | 58 | 13.1 Communication Theory | Communications | 2 | 30 | Light review of 13.1 Communication Theory. No heavy problem solving. | 0 | 0
7 | 2026-05-23 | Saturday | Family | 45 | 4 | 0 | 0 | 2 | 30 | 8.1 Sampling | Signal Processing | 2 | 45 | Light review of 8.1 Sampling. No heavy problem solving. | 0 | 0
Formulas:
Date = [Date, row above]+1